## ProductBackLog
Project Name: RePlate Group Members: Eren PAMUK , Hayrünisa TOPRAK , Hüseyin Alp ERCANDANOĞLU , Hüseyin ESEN , Beyza Makbule YILDIRIM , Ramazan YILDIRIM , Aylin DÖNMEZ
# | Product BackLog
1 | Database (PostgreSQL) planning for users, businesses, municipalities, and product listings
2 | Creation of separate registration/login forms and personal profiles for municipalities, businesses, and clients
3 | Allowing businesses to declare surplus food details (category, quantity, expiration date, photo, pickup time).
4 | Integration of Google Maps API to display surplus food on an interactive map with a maximum GPS error margin of 25 meters.
5 | Implementation of search and filter functionality by category, price, distance, expiration date, and stock.
6 | Setup of a reservation system with real-time stock deduction and unique QR code generation
7 | Allowing users to cancel reservations up to 30 minutes before pickup, making the stock available again
8 | Secure processing of in-app payments using external payment providers for discounted surplus food purchases.
9 | Implementation of a two-stage redistribution model that automatically transfers uncollected food to municipal distribution centers.
10 | Development of a municipal management panel to track incoming transfers and process user pickups.
11 | Development of personal impact dashboards displaying total food saved (kg), money saved (TL), and CO2 emission reduction.
12 | Provision of statistical dashboards for busine sses and municipalities to analyze waste reduction and regional food data.
13 | Implementation of automatic dynamic pricing suggestions for products within 24 hours of their expiration date
14 | Sending push notifications for new surplus products, price drops, products approaching their expiration date, and favorite branches.
15 | Addition of donation features allowing users to donate meals for people in need and pet food for animal shelters.
16 | Implementation of AES-256 encryption and SSL/TLS protocols for all user, payment, and reservation data.
17 | Optimization of the application for Android 10+ and iOS 14+ on devices with at least 4GB RAM. (Lower limits are kept this way for backward compatibility).
18 | Ensuring the system supports 10,000 concurrent users with search/filter response times below 3 seconds.
19 | Implementation of automatic daily backups and ensuring the system can restart itself within 5 minutes in case of a crash.
20 | Designing the system with a modular architecture for future AI prediction updates and feature expansions.

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Database (PostgreSQL) planning for users, businesses, municipalities, and product listings. | In Progress | High | 2027-11-01 | 2027-11-04 | 4 | Implement JWT-based authentication. Ensure strict separation of privileges between Customer, Business, and Municipality roles.
Developer | Creation of separate registration/login forms and personal profiles for all users. | Ready to Start | High | 2027-11-05 | 2027-11-10 | 6 | Make sure bussinesses, users, and the city have their own private login/registration screens and profiles.
Developer | Implementation of AES-256 encryption and SSL/TLS protocols for all user/payment data | Ready to Start | High | 2027-11-01 | 2027-11-03 | 3 | Using the AES-256 encryption since this system will also contain information and data of people with high level of authority
10
BACKLOG
As a Social Services Director from the Municipality, I would need to register using a registration form for municipality users for access to more features
STATUS: Ready to Start
DEV 1
As a city staff member ,I want the system to handle requests with fast precision and accuracy and also a strict separation between customers and businesses
STATUS: Ready to Start
DEV 2
As a user I want my personal data and payment information to be protected well so that I can rescue food and support my community with total peace of mind, knowing that my data is safe and secure.
STATUS : Ready to Start
Dev 3

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Allowing businesses to declare surplus food details (category, qty, exp date, photo) | Not Started | Medium | 2027-11-15 | 2027-11-18 | 4 | Implement secure image uploads (e.g., via AWS S3). Add strict frontend/backend validation so businesses cannot set expiration dates in the past.
Developer | Integration of Google Maps API to display surplus food with 25m GPS error margin. | Not Started | Medium | 2027-11-15 | 2027-11-19 | 5 | Utilize Geocoding and Places APIs. Optimize API calls by clustering markers to keep cloud costs low and performance high.
Developer | Implementation of search and filter functionality by category, price, distance, and stock. | Not Started | Medium | 2027-11-12 | 2027-11-18 | 5 | Leverage PostGIS functions (like ST_Distance) for fast, radius-based location filtering. Index categories and prices heavily.
Developer | Setup of a reservation system with real-time stock deduction and unique QR generation. | Not Started | High | 2027-11-17 | 2027-11-18 | 2 | Implement optimistic locking in the database to prevent double-booking items. Use a lightweight library for QR generation.
Developer | Allowing users to cancel reservations up to 30 minutes before pickup. | Not Started | Low | 2027-11-17 | 2027-11-18 | 2 | Set up a background worker to automatically return canceled stock to the public pool if canceled within the allowed window.
8
BACKLOG
As a business owner, I want to be able to list the surplus food I have in my hands and upload its expiration date and picture.
STATUS: Not Started
As customer, I want to be able to cancel my order in case I change my mind with it.
STATUS: Not Started
DEV 1
As a customer, I want to be able to reserve a purchase online and a QR code verification along with it so that it can be confirmed the order is mine.
STATUS: Not Started
DEV 5
DEV 1
As a user , I want access to a map system that allows me to find the surplus food by searching the areas in proximity so I can see where I can get discounted stuff close to me
DEV 2

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Secure processing of in-app payments using external providers for surplus food. | Not Started | High | 2027-11-22 | 2027-11-28 | 7 | Integrate a secure payment gateway like Stripe or Iyzico. Set up robust webhook handlers to update order statuses upon payment success/failure.
Developer | Implementation of a two-stage redistribution model (auto-transfer to municipalities). | Not Started | Medium | 2027-12-01 | 2027-12-03 | 3 | Create modules that scan for expired user-pickup times and automatically flag the items for municipal transfer.
Developer | Development of a municipal management panel to track incoming transfers and process user pickups. | Not Started | Medium | 2027-11-22 | 2027-11-24 | 3 | A screen for city staff to track scaned user QR codes and food pickups.
Developer | Sending push notifications for new products, price drops, and favorite branches. | Not Started | Medium | 2027-11-25 | 2027-11-26 | 2 | Notify a user when a branch nearby has a deal
Developer | Addition of donation features for people in need and animal shelters. | Not Started | Low | 2027-11-29 | 2027-11-30 | 2 | User should be able to make donations by sending donations or by purchasing food/supplies
Developer | Designing the system with a modular architecture for future AI prediction updates. | Not Started | High | 2027-12-01 | 2027-12-02 | 2 | Create clean system architecture for the pricing and recommendation modules so AI models can easily replace rule-based logic later.
12
BACKLOG
As a user from the municipality , in case a product is not collected on time and is on it’s way to a central branch / redistribution center , I want to be notified and I also need a management panel to see to where an order goes
STATUS: Not Started
As a user , I want to have a secure payment gateway like Stripe or Iyzico so I can donate to shelters voluntarily while being sure my donation isnt redirected.
STATUS: Not Started
DEV 4
DEV 3
As a user , I want a feature that notifies me whenever a product I need is available in a nearby branch I can know about it as soon as possible
STATUS: Not Started
DEV 4

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Development of personal impact dashboards (food saved, money saved, CO2 reduction). | Not Started | Low | 2027-12-10 | 2027-12-11 | 2 | Calculate metrics dynamically from historical reservation data. Use lightweight charting libraries (like Chart.js) for the UI.
Developer | Provision of statistical dashboards for businesses and municipalities to analyze waste. | Not Started | Low | 2027-12-10 | 2027-12-11 | 2 | Return data that informs which and how much of the food and supplements were unconsumed or purchased , resulting in waste
Developer | Implementation of automatic dynamic pricing suggestions for products 24h from expiry. | Not Started | Medium | 2027-12-08 | 2027-12-09 | 2 | Business owner shall be regularly receiving updates on the product thats getting close to expire throughout the 24 hours
Developer | Test optimization of the application for Android 10+ and iOS 14+ on 4GB RAM devices. | Not Started | Medium | 2027-12-10 | 2027-12-13 | 4 | Test if the app runs smoothly even on devices that fulfill only the minimal requirements and make sure it runs compatible with all devices
Developer | Testing if the system supports 10,000 concurrent users with 3s response times. | Not Started | High | 2027-12-16 | 2027-12-21 | 6 | Test the app to stay fast even when thousands of people use it at once.
Developer | Implementation of automatic daily backups and 5-minute crash restart capability. | Not Started | Medium | 2027-12-24 | 2027-12-27 | 4 | Save a copy of all data every day and make a plan to restart quickly if it crashes.
Developer | Testing for Security Concerns | Not Started | High | 2027-12-30 | 2028-01-04 | 6 | Run tests to see how well the system is designed without security vulnerabilities or exploits.
4
BACKLOG
As a user , I would want the system up all the times , no matter how many users are active at the same time without giving any loading or performance issues
As someone working as city staff , I would want to be able to track which food is being wasted the most and what products are more bound to go to trash without being sold.
STATUS: Not Started
DEV 5
DEV 6
AS a business owner , I would want to be notified whenever there is short (24 hrs )time left before my product expires so it can be make it to good hands in time.
STATUS: Not Started
DEV 1

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here